## Commissioning checklist
Commissioning checklist
One subsystem, from mechanical completion to handover. Yellow cells are for you to fill in. Free template from Deskely · deskely.com/resources/commissioning-checklist
Project |  | System
Subsystem |  | Commissioning lead
Progress
| Done | 0 | Open | 0 | of | 31
No. | Check | Status | Record or reference | By | Date | Remarks
MECHANICAL COMPLETION
1 | All A ITRs (construction checks) for the subsystem signed |  | ITR register
2 | Pressure tests complete and test packs closed, spades and blinds removed, items reinstated |  | Test packs
3 | Flushing and cleaning complete and signed |  | Flushing records
4 | Cables installed, terminated and insulation resistance tested |  | Cable schedule, ITRs
5 | Equipment installed, aligned and grouted where required |  | Installation ITRs
6 | Instruments installed to hook-up drawings, impulse lines leak tested |  | Instrument ITRs
7 | Insulation, painting and fireproofing complete, or listed as punch |  | Punch list
8 | All A punch items closed; B items listed and accepted |  | Punch list
9 | As-built red-line markups submitted |  | Redlines
10 | Mechanical completion certificate signed |  | MC certificate
PRE-COMMISSIONING
11 | Loop checks complete for every instrument loop |  | Loop check sheets
12 | Motor solo runs and direction of rotation checked |  | B ITRs
13 | Protection relay settings applied and tested |  | Relay test reports
14 | Actuated valves stroked, stroke times and fail positions checked |  | Valve function tests
15 | Safety valves set, certified, installed and locked in position |  | PSV certificates
16 | Lubrication and first fill of oils and chemicals complete |  | Lube records
17 | All B ITRs signed |  | ITR register
18 | Ready for commissioning certificate signed |  | RFC certificate
COMMISSIONING
19 | Commissioning procedures approved and issued |  | Procedures
20 | Permits, isolations and system boundaries in place |  | Permit register
21 | Utilities available: power, instrument air, cooling water, nitrogen |  | Utility status
22 | Control and safety system logic tested against the cause and effect |  | C&E test records
23 | Fire and gas detection tested |  | F&G test records
24 | Functional and performance tests complete, results recorded |  | Test reports
25 | Operators and maintainers trained; O&M manuals available |  | Training records
26 | Pre-startup safety review complete where required |  | PSSR checklist
27 | Ready for start-up certificate signed |  | RFSU certificate
HANDOVER
28 | Remaining punch items agreed with the owner, with owners and dates |  | Punch list
29 | Handover dossier complete: certificates, ITRs, test records, vendor documents, as-builts |  | Dossier index
30 | Spare parts and special tools handed over |  | Spares list
31 | Handover certificate signed |  | Handover certificate
Sign-off | Name | Company |  | Signature |  | Date
Construction
Commissioning
Owner