## Handover dossier index
Handover dossier index
Yellow cells are for you to fill in. Free template from Deskely · deskely.com/resources/handover-document-template
Project |  | System |  | Subsystem
Handed over by |  | Received by |  | Planned handover date
Progress
No. | Document | Required | Status | Reference or file | Remarks
1. CERTIFICATES
1.1 | Mechanical completion certificates | Yes
1.2 | Ready for commissioning certificates | Yes
1.3 | Ready for start-up certificate | Yes
1.4 | Handover certificate | Yes
2. REGISTERS
2.1 | Tag register for the system | Yes
2.2 | ITR register (A, B and C) | Yes
2.3 | Punch list with the open items agreed and dated | Yes
3. INSPECTION AND TEST RECORDS
3.1 | Construction ITRs (A) | Yes
3.2 | Pre-commissioning ITRs (B) | Yes
3.3 | Commissioning and function test records | Yes
3.4 | Pressure test packs and certificates | Yes
3.5 | Insulation resistance and electrical test reports | Yes
3.6 | Loop check records | Yes
3.7 | Instrument calibration certificates | Yes
3.8 | Safety valve certificates | Yes
4. QUALITY RECORDS
4.1 | Material certificates (EN 10204 3.1) | Yes
4.2 | Weld maps, weld logs and NDT reports | Yes
4.3 | Non-conformance reports, closed or agreed | Yes
4.4 | Painting and coating reports | Yes
5. AS-BUILT DRAWINGS
5.1 | P&IDs | Yes
5.2 | Isometrics | Yes
5.3 | Single line diagrams and cable schedules | Yes
5.4 | Hazardous area drawings and Ex register | Yes
6. VENDOR DOCUMENTATION
6.1 | Datasheets | Yes
6.2 | Installation, operation and maintenance manuals | Yes
6.3 | FAT and SAT reports | Yes
6.4 | Vendor certificates and warranties | Yes
7. OPERATIONS AND MAINTENANCE
7.1 | Operating procedures | Yes
7.2 | Maintenance plan | Yes
7.3 | Spare parts list and special tools | Yes
7.4 | Training records | Yes
8. PRESERVATION
8.1 | Preservation records up to handover | Yes
Sign-off |  | Name | Company | Signature | Date
Handed over by
Received by

## Handover checklist
Handover checklist
What has to be true on the day care, custody and control passes to the owner.
Project |  | System | Handover date
No. | Check | Status | Reference | By | Date
1 | All category A punch items closed
2 | Category B items agreed with the owner, with owners and dates
3 | RFSU certificate signed for the system
4 | Energised and live status of the system agreed and marked
5 | Isolations, permits and lock-outs transferred to the owner
6 | Keys, passwords, licences and software back-ups handed over
7 | Spare parts, special tools and first fills delivered
8 | Operators and maintainers trained
9 | Warranty start dates agreed
10 | Completions dossier reviewed and accepted
11 | Handover certificate signed
Sign-off |  | Name | Company | Signature | Date
Contractor
Owner