## Piping installation inspection
Piping installation inspection checklist
Yellow cells are for you to fill in. Free template from Deskely · deskely.com/resources/piping-inspection-checklist
Project |  | Line number | Isometric and revision
System / subsystem |  | Piping class | Test pack
Progress
No. | Check | Result | Reference | By | Date
MATERIALS AND WELDING
1 | Pipe, fittings, flanges and valves to the piping class
2 | Welding complete; weld log and weld map up to date
3 | NDT and PWHT complete to the specified extent
4 | Spec breaks at the right location
ROUTING AND SUPPORTS
5 | Routing and elevations to the isometric
6 | Supports, guides and anchors to the support drawings and in contact
7 | Shoes and slide plates free to move
8 | Spring supports set; travel stops left in until after the test
9 | Slopes as required; no pockets where not allowed
FLANGED JOINTS
10 | Flange alignment and parallelism within tolerance
11 | Gaskets to the specification
12 | Bolting material and length correct; full thread engagement
13 | Bolts tightened to the joint procedure (torque or tensioning record)
VALVES AND IN-LINE ITEMS
14 | Valves installed with the flow direction correct
15 | Handwheels and actuators accessible and orientated correctly
16 | In-line instruments and orifices installed or spooled out for the test
17 | Vents at high points and drains at low points
18 | Small-bore branches braced
BEFORE THE TEST PACK
19 | Clearances and access for operation and maintenance
20 | Internal cleanliness; no debris
21 | Temporary items removed or listed
22 | Redlines marked on the isometric
Sign-off |  | Name | Company | Signature | Date
Contractor QC
Client