## Pre-commissioning checklist
Pre-commissioning checklist
Yellow cells are for you to fill in. Free template from Deskely · deskely.com/resources/pre-commissioning-checklist
Project |  | System | Subsystem
Commissioning lead |  | MC certificate date | Target RFC date
Progress
No. | Activity | Status | Record | By | Date
PIPING AND MECHANICAL
1 | Flushing or air blowing complete and accepted |  | Flushing records
2 | Chemical cleaning or pickling, where specified |  | Cleaning report
3 | Pressure test packs closed and reinstated |  | Test packs
4 | Drying and nitrogen purging, where required |  | Dew point records
5 | Leak test with service medium or nitrogen |  | Leak test record
6 | Rotating equipment aligned |  | Alignment report
7 | Lube oil flushing and first fill of oils and chemicals |  | Lube records
8 | Vessel and tank internals inspected and boxed up |  | Box-up certificate
9 | Temporary strainers and screens installed |  | Strainer register
ELECTRICAL
10 | Cable insulation resistance and continuity tested |  | IR test reports
11 | Terminations and torque checked |  | Termination ITRs
12 | Earthing and bonding tested |  | Earthing test report
13 | Protection relay settings applied and tested |  | Relay test reports
14 | Transformer tests: ratio, winding resistance, insulation |  | Transformer test report
15 | Switchgear function and interlock checks |  | Switchgear ITRs
16 | Motor solo run and direction of rotation |  | B ITRs
17 | UPS and battery tests |  | Battery discharge test
INSTRUMENTATION AND CONTROL
18 | Instruments calibrated |  | Calibration certificates
19 | Loop checks complete |  | Loop check sheets
20 | Control and on/off valves stroked, fail positions confirmed |  | Valve test records
21 | Safety valves set, certified and installed |  | PSV certificates
22 | Control and safety system I/O checked |  | I/O check records
23 | Cause and effect logic tested cold |  | C&E test records
24 | Fire and gas detectors tested |  | F&G test records
HVAC AND TELECOMS
25 | Fans, dampers and air balance checked |  | HVAC test sheets
26 | Telecom systems (PA/GA, CCTV, radio) checked |  | Telecom ITRs
CLOSE-OUT
27 | All pre-commissioning (B) ITRs signed |  | ITR register
28 | Open punch items listed and categorised |  | Punch list
29 | Ready for commissioning certificate signed |  | RFC certificate
Sign-off |  | Name | Company | Signature | Date
Construction
Commissioning
Client