## PSSR checklist
Pre-startup safety review (PSSR) checklist
Yellow cells are for you to fill in. Free template from Deskely · deskely.com/resources/pre-startup-safety-review
Facility or unit |  | System / scope | PSSR date
PSSR team leader |  | MOC or project reference | Planned start-up
Progress
No. | Check | Confirmed | Evidence | By | Date
CONSTRUCTION
1 | Built to the latest P&IDs and design specifications
2 | Mechanical completion certified; category A punch closed
3 | Pressure tests and NDT complete
SAFETY SYSTEMS
4 | Relief valves installed, set, tagged and locked correctly
5 | Safety instrumented functions tested
6 | Fire and gas detection and firefighting systems in service
PROCESS SAFETY INFORMATION
7 | P&IDs, datasheets, relief design basis and safe operating limits updated to as-built
HAZARD REVIEWS
8 | PHA or HAZOP recommendations closed, or formally deferred with justification
MANAGEMENT OF CHANGE
9 | All MOCs for the scope implemented and closed
10 | Temporary changes removed
PROCEDURES
11 | Operating and start-up procedures issued and approved
12 | Emergency and maintenance procedures issued and approved
TRAINING
13 | Operators trained on the new or changed process
14 | Maintenance staff trained
EMERGENCY READINESS
15 | Emergency response plan updated
16 | Escape routes clear; safety showers, eyewash and PPE in place
HOUSEKEEPING AND ISOLATION
17 | Temporary equipment, blinds and scaffolding removed
18 | Isolations and permits closed or transferred
Sign-off |  | Name | Signature | Date
PSSR team leader
Operations
Process safety

## PSSR findings
PSSR findings
Before start-up: must be closed before start-up. After start-up: may be closed later, with an owner and a date.
No. | Finding | Category | Owner | Due | Status | Closed
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22