## Punch list
Punch list
Free template from Deskely · deskely.com/resources/punch-list-template · Yellow cells are for you to fill in.
Project | [5 empty] | Contract / PO |  |  |  |  | Open A items | 1
System | [5 empty] | Subsystem |  |  |  |  | Open items | 1
Walkdown date | [5 empty] | Prepared by |  |  |  |  | Total items | 1
Item no. | Tag | System | Subsystem | Discipline | Location | Description | Category | Raised by | Date raised | Action by | Due date | Status | Cleared by | Date cleared | Verified by | Days open | Photo / ref. | Remarks
1001-P-0001 | 20-PT-1001 | 20 | 20-01 | Instrument | Module M2, deck 2 | Example row, delete before use. Cable gland not tightened at the junction box end. | A | Inspector, Contractor | 2026-10-01 | E&I subcontractor | 2026-10-15 | Open |  |  |  | 28 | IMG_0412.jpg
Formulas:
Days open = IF([Date raised]="","",IF([Date cleared]="",TODAY(),[Date cleared])-[Date raised])

## Summary
Punch summary
Counts update from the Punch list sheet. Nothing to fill in here.
Category | Open | Ready for verification | Closed | Rejected | Total | Not closed
A | 1 | 0 | 0 | 0 | 1 | 1
B | 0 | 0 | 0 | 0 | 0 | 0
C | 0 | 0 | 0 | 0 | 0 | 0
D | 0 | 0 | 0 | 0 | 0 | 0
Total | 1 | 0 | 0 | 0 | 1 | 1
No category | 0 | items with a description but no category
Closed | 0%
Overdue | 1
Discipline | Open | Open A | Closed | Total
Piping | 0 | 0 | 0 | 0
Mechanical | 0 | 0 | 0 | 0
Electrical | 0 | 0 | 0 | 0
Instrument | 1 | 1 | 0 | 1
Telecom | 0 | 0 | 0 | 0
HVAC | 0 | 0 | 0 | 0
Structural | 0 | 0 | 0 | 0
Process | 0 | 0 | 0 | 0
Safety | 0 | 0 | 0 | 0
Painting / insulation | 0 | 0 | 0 | 0
Architectural | 0 | 0 | 0 | 0
Other | 0 | 0 | 0 | 0

## How to use
How to use this punch list
1 | Fill in the yellow cells at the top of the Punch list sheet: project, system, subsystem, walkdown date.
2 | Delete the grey example row, then add one row per item. Category, Discipline and Status are drop-downs.
3 | Give every item a tag, so it rolls up to its subsystem and the certificate it blocks.
4 | When the work is done, set Status to Ready for verification. The inspector or client verifies it and sets Closed.
5 | Closed rows turn grey. Open A items show in red, and overdue due dates in bold red.
6 | The Summary sheet counts items by category, status and discipline. It updates by itself.
Punch categories
A | Must be cleared before the next milestone, usually mechanical completion. Safety items, missing or wrong work, anything that stops testing or energising.
B | Does not stop the next milestone. Must be cleared before commissioning is complete or the system is handed over.
C | Minor or cosmetic. Cleared before final acceptance, or carried into operations by agreement.
D | Optional. Some projects use D for items outside the contract scope or waiting for a client decision.
The exact definitions come from your project completions procedure, which takes precedence over this sheet.
Columns
Item no. | Unique number, e.g. 1001-P-0001
Tag | Equipment, line, cable or instrument tag
System
Subsystem
Discipline | Pick from the list
Location | Module, deck, room or grid
Description | What is wrong or missing, and where
Category | A, B, C or D
Raised by | Name and company
Date raised
Action by | Party who clears it
Due date
Status | Pick from the list
Cleared by
Date cleared
Verified by | Inspector or client
Days open | Calculated
Photo / ref. | Photo file name or document number
Remarks
Status flow
Open → Ready for verification → Closed. Rejected means the fix was not accepted and the item goes back to Open.
About
Free punch list template from Deskely, free to use and change. Guide: https://deskely.com/resources/punch-list-template
On a live project, Deskely raises punch items on a phone or tablet, offline, with photos, against the tag, and shows which items block each certificate: https://deskely.com/punch-list-software

## Lists
Category | Discipline | Status | Edit these lists to change the drop-downs on the Punch list sheet (keep the same number of rows or fewer).
A | Piping | Open
B | Mechanical | Ready for verification
C | Electrical | Closed
D | Instrument | Rejected
Telecom
HVAC
Structural
Process
Safety
Painting / insulation
Architectural
Other