## Valve test certificate
Valve test certificate
Yellow cells are for you to fill in. Free template from Deskely · deskely.com/resources/valve-test-certificate
Project |  | Certificate number |  | Date
Valve tag |  | Valve type |  | Size and pressure class
Manufacturer |  | Serial number |  | Body and trim material
Test standard |  | Test medium |  | Gauge number and calibration due
API 598: shell test at 1.5 times the rated pressure at 38 °C; high-pressure closure test at 1.1 times; low-pressure closure test with air or gas at 4 to 7 bar (60 to 100 psi). Minimum test durations and allowed seat leakage depend on valve size and type; take them from the standard or your specification.
No. | Test | Test pressure | Duration | Leakage allowed | Leakage measured | Result
1 | Shell test (hydrostatic)
2 | Backseat test (where applicable)
3 | High-pressure closure test, side A
4 | High-pressure closure test, side B
5 | Low-pressure closure test (gas), side A
6 | Low-pressure closure test (gas), side B
CHECKS
No. | Check |  |  | Status | Remarks
1 | Body marking and tag plate match the datasheet
2 | End connections and faces undamaged
3 | Opens and closes fully; position indicator correct
4 | Actuator: stroke time and fail position (actuated valves)
5 | Valve drained and dried after test; ends protected
Certificate
We certify that the valve above has been tested in accordance with the stated standard and the results recorded, and that it is accepted.
Sign-off |  | Name |  | Signature | Date
Tested by
Witnessed by

## Valve test register
Valve test register
One line per valve tested on site.
Valve tag | Type | Size | Class | Test date | Shell | Seat | Backseat | Certificate no. | Remarks